## Sheet1
Input Total Hours ----> |  | 1000 |  | Input ID Hourly |  | 100
|  |  |  | Input Developer Rate |  | 100
|  |  |  | Input Graphic Artist Rate |  | 100
|  |  |  | Input Media Spec. Rate |  | 100
Analysis/Concepting |  | Hours | Dollars | Input Proj. Mgr. Rate |  | 100
Analysis | 3% | 30 | 3000
Design for PT | 2% | 20 | 2000
Prototype | 4% | 40 | 4000
Scope Definition | 1% | 10 | 1000
Total | 10% | 100 | 10000
Design |  | Hours | Dollars
Detailed Outline | 4% | 40 | 4000
Objectives | 2% | 20 | 2000
SB's | 13% | 130 | 13000
Test ?'s | 2% | 20 | 2000
Total | 21% | 210 | 21000
Development
Logic Dev. | 24% | 240 | 24000
Graphics | 12% | 120 | 12000
A/V | 6% | 60 | 6000
Proj. Mgmt. | 15% | 150 | 15000
Total | 57% | 570 | 57000
Delivery |  |  |  |  | Hours | Dollars
QA | 4% | 40 | 4000 | Designer | 300 | 30000
Beta Test | 4% | 40 | 4000 | Developer | 370 | 37000
Packaging | 2% | 20 | 2000 | Graphics | 120 | 12000
Documentation | 2% | 20 | 2000 | Media Spec. | 60 | 6000
Total | 12% | 120 | 12000 | Proj. Mgr. | 150 | 15000
Total | 100% | 1000 | 100000 |  | 1000 | 100000